## Product Backlog
SL | Sprint | Sprint Period | Sprint Goal | Tasks Planned | Tasks Completed | Deliverables | Status
1 | Sprint 1 | 18 Feb 2026 – 24 Feb 2026 | Requirement analysis and project planning | Requirement gathering, problem understanding, system scope definition, tech stack finalization | Requirements documented, architecture drafted | Requirement Specification, High-level Architecture | Completed
2 | Sprint 2 | 25 Feb 2026 – 03 Mar 2026 | Knowledge base design and data preparation | Knowledge base schema design, sample ticket & article collection, FAISS vector store setup | Data schema finalized, initial dataset prepared, FAISS index created | Structured knowledge base, sample data, faiss_index folder | Completed
3 | Sprint 3 | 04 Mar 2026 – 10 Mar 2026 | RAG engine & embedding pipeline | Build rag_engine.py with OllamaEmbeddings (tinyllama), document ingestion, chunk splitting | RAG engine implemented, ingest.py working, FAISS index populated | rag_engine.py, ingest.py, processed PDFs | Completed
4 | Sprint 4 | 11 Mar 2026 – 17 Mar 2026 | LLM engine & AI resolution generation | Build llm_engine.py with llama3.2:1b, prompt engineering, confidence scoring logic | LLM engine generating resolutions, confidence & status logic working | llm_engine.py with analyze_ticket(), confidence scoring | Completed
5 | Sprint 5 | 18 Mar 2026 – 24 Mar 2026 | Database layer & auth service | Build database.py (SQLite schema, tickets/users/gap tables), auth_service.py with bcrypt | DB initialized, login/register working, default users seeded | database.py, auth_service.py, support_tickets.db | Completed
6 | Sprint 6 | 25 Mar 2026 – 31 Mar 2026 | Ticket service & knowledge gap detection | Build ticket_service.py orchestration, knowledge gap event tracking, alert logic | Ticket submission pipeline working end-to-end, gap events logged | ticket_service.py, knowledge_gap_events table | Completed
7 | Sprint 7 | 01 Apr 2026 – 07 Apr 2026 | Streamlit UI – frontend development | Build app.py with login/signup page, New Incident tab, My History tab, admin view | Fully functional web UI, dark-mode CSS, session state management | app.py (Streamlit), custom CSS, run.py launcher | Completed
8 | Sprint 8 | 08 Apr 2026 – 14 Apr 2026 | Testing, optimization & documentation | End-to-end testing via test_backend.py, bug fixing, config.py env tuning, project docs | Stable system, all tests passing, documentation complete | test_backend.py results, project_modules_guide.md, final app | Completed

## Sprint Backlog
NOTE: Task sizing should be between 0.5 to 12 hours ¦ Assignee: Mohd Amaan Khan
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Activity | Status | Estimated Effort (hrs) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
SPRINT 1 BACKLOG ¦ 18 Feb 2026 – 24 Feb 2026 ¦ Assignee: Mohd Amaan Khan
US-01 | T-01 | Gather functional requirements & define problem scope | 18 Feb 2026 | 18 Feb 2026 | Analysis | Completed | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0
US-01 | T-02 | Define tech stack (Python, Ollama, FAISS, Streamlit, SQLite) | 18 Feb 2026 | 19 Feb 2026 | Planning | Completed | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0
US-01 | T-03 | Design high-level architecture diagram | 19 Feb 2026 | 20 Feb 2026 | Design | Completed | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0
US-01 | T-04 | Document requirement specification | 20 Feb 2026 | 21 Feb 2026 | Documentation | Completed | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0
US-01 | T-05 | Create project folder structure & initialize git | 21 Feb 2026 | 21 Feb 2026 | Setup | Completed | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0
SPRINT 2 BACKLOG ¦ 25 Feb 2026 – 03 Mar 2026 ¦ Assignee: Mohd Amaan Khan
US-02 | T-06 | Design SQLite schema for tickets, users, knowledge_gap_events | 25 Feb 2026 | 25 Feb 2026 | Design | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-07 | Collect sample IT support tickets & knowledge articles | 25 Feb 2026 | 26 Feb 2026 | Research | Completed | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0
US-02 | T-08 | Set up data/raw and data/processed directory structure | 26 Feb 2026 | 26 Feb 2026 | Setup | Completed | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0
US-02 | T-09 | Test PDF ingestion with sample documents | 27 Feb 2026 | 28 Feb 2026 | Testing | Completed | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG ¦ 04 Mar 2026 – 10 Mar 2026 ¦ Assignee: Mohd Amaan Khan
US-03 | T-10 | Implement OllamaEmbeddings class (tinyllama model) | 04 Mar 2026 | 04 Mar 2026 | Development | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-11 | Build ingest_documents() with FAISS index creation | 05 Mar 2026 | 05 Mar 2026 | Development | Completed | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0
US-03 | T-12 | Implement get_relevant_context() with similarity scoring | 06 Mar 2026 | 06 Mar 2026 | Development | Completed | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0
US-03 | T-13 | Build ingest.py CLI with tqdm progress bars | 07 Mar 2026 | 07 Mar 2026 | Development | Completed | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0
US-03 | T-14 | Run ingest on IT-SOP and Network Config PDFs | 08 Mar 2026 | 08 Mar 2026 | Testing | Completed | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0
SPRINT 4 BACKLOG ¦ 11 Mar 2026 – 17 Mar 2026 ¦ Assignee: Mohd Amaan Khan
US-04 | T-15 | Implement analyze_ticket() with RAG context injection | 11 Mar 2026 | 12 Mar 2026 | Development | Completed | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-16 | Build confidence scoring logic (_calculate_confidence) | 12 Mar 2026 | 13 Mar 2026 | Development | Completed | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0
US-04 | T-17 | Implement resolution_status threshold (resolved/tentative) | 13 Mar 2026 | 14 Mar 2026 | Development | Completed | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0
US-04 | T-18 | Add model availability check & auto-pull logic | 15 Mar 2026 | 15 Mar 2026 | Development | Completed | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0
SPRINT 5 BACKLOG ¦ 18 Mar 2026 – 24 Mar 2026 ¦ Assignee: Mohd Amaan Khan
US-05 | T-19 | Build database.py with init_db(), create_user(), get_user() | 18 Mar 2026 | 19 Mar 2026 | Development | Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-20 | Implement auth_service.py with bcrypt hashing | 19 Mar 2026 | 20 Mar 2026 | Development | Completed | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0
US-05 | T-21 | Add column migration logic (_ensure_ticket_columns) | 20 Mar 2026 | 21 Mar 2026 | Development | Completed | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0
US-05 | T-22 | Test user registration, login, default seed data | 22 Mar 2026 | 22 Mar 2026 | Testing | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0
SPRINT 6 BACKLOG ¦ 25 Mar 2026 – 31 Mar 2026 ¦ Assignee: Mohd Amaan Khan
US-06 | T-23 | Build ticket_service.py submit_ticket() orchestration | 25 Mar 2026 | 26 Mar 2026 | Development | In Progress | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-24 | Implement knowledge gap event tracking & grouping | 26 Mar 2026 | 27 Mar 2026 | Development | In Progress | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0
US-06 | T-25 | Add get_all_tickets() and get_user_tickets() admin functions | 28 Mar 2026 | 29 Mar 2026 | Development | Planned | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0
US-06 | T-26 | Integrate config.py env-based threshold tuning | 30 Mar 2026 | 31 Mar 2026 | Development | Planned | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
SPRINT 7 BACKLOG ¦ 01 Apr 2026 – 07 Apr 2026 ¦ Assignee: Mohd Amaan Khan
US-07 | T-27 | Build Streamlit login/signup UI page | 01 Apr 2026 | 02 Apr 2026 | Development | Planned | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-28 | Build New Incident submission form & AI result display | 02 Apr 2026 | 03 Apr 2026 | Development | Planned | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-29 | Build My History tab with expandable tickets | 04 Apr 2026 | 05 Apr 2026 | Development | Planned | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-30 | Add dark-mode CSS styling (Inter font, blue #3b82f6) | 06 Apr 2026 | 06 Apr 2026 | Design | Planned | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 8 BACKLOG ¦ 08 Apr 2026 – 14 Apr 2026 ¦ Assignee: Mohd Amaan Khan
US-08 | T-31 | Run test_backend.py automated test suite | 08 Apr 2026 | 09 Apr 2026 | Testing | Planned | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-32 | Fix all bugs found during testing | 09 Apr 2026 | 11 Apr 2026 | Bug Fix | Planned | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-33 | Optimize LLM prompt for better resolution quality | 11 Apr 2026 | 12 Apr 2026 | Optimization | Planned | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-34 | Finalize project_modules_guide.md documentation | 13 Apr 2026 | 14 Apr 2026 | Documentation | Planned | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand Up Meeting
DAILY STAND-UP LOG ¦ Project: AI Smart Support & Ticket Resolution ¦ Mohd Amaan Khan
Sprint | Day / Date | What I Did Yesterday | What I'll Do Today | Impediments / Blockers
1 | 18 Feb 2026 | Project kickoff | Requirements gathering | None
1 | 19 Feb 2026 | Requirements gathered | Tech stack selection | None
1 | 20 Feb 2026 | Tech stack finalized | Architecture design | None
1 | 21 Feb 2026 | Architecture drafted | Requirement spec doc | None
1 | 22 Feb 2026 | Spec doc written | Folder setup & git init | None
2 | 25 Feb 2026 | Folder structure ready | DB schema design | None
2 | 26 Feb 2026 | DB schema designed | Sample data collection | None
2 | 27 Feb 2026 | Data collected | Test PDF ingestion | Ollama model slow on CPU
2 | 28 Feb 2026 | PDF ingestion tested | Finalize sprint 2 | None
3 | 04 Mar 2026 | Sprint 2 delivered | Implement OllamaEmbeddings | None
3 | 05 Mar 2026 | Embeddings working | Build ingest_documents() | FAISS install took extra time
3 | 06 Mar 2026 | Ingest working | Implement get_relevant_context() | None
3 | 07 Mar 2026 | Context retrieval working | Build ingest.py CLI | None
3 | 08 Mar 2026 | CLI script done | Run ingest on sample PDFs | None
4 | 11 Mar 2026 | RAG engine ready | Build analyze_ticket() | None
4 | 12 Mar 2026 | analyze_ticket() done | Confidence scoring | None
4 | 13 Mar 2026 | Confidence scoring done | Resolution status thresholds | None
4 | 15 Mar 2026 | LLM engine complete | Model pull logic | None
5 | 18 Mar 2026 | LLM engine ready | Build database.py | None
5 | 19 Mar 2026 | DB layer done | Build auth_service.py | None
5 | 20 Mar 2026 | Auth service done | Column migration logic | None
5 | 22 Mar 2026 | Migration logic done | Test auth & DB | None
6 | 25 Mar 2026 | Auth & DB ready | Build ticket_service.py | None
6 | 26 Mar 2026 | submit_ticket() in progress | Knowledge gap tracking | None
6 | 27 Mar 2026 | Gap tracking in progress | Continue gap logic | Complexity higher than estimated

## Retrospection
SPRINT RETROSPECTION ¦ Developer: Mohd Amaan Khan ¦ AI Smart Support & Ticket Resolution
SL # | Sprint # | Sprint Start Date | Sprint End Date | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | Sprint 1 | 18 Feb 2026 | 24 Feb 2026 | Create detailed sub-tasks for each requirement item | Spending too much time on vague goal definitions | Systematic requirement documentation approach | Added task breakdown template for next sprint
2 | Sprint 2 | 25 Feb 2026 | 03 Mar 2026 | Test embeddings earlier in the sprint cycle | Waiting until end of sprint to validate ingestion pipeline | Good schema-first design approach | Scheduled embedding tests on Day 2 of each sprint
3 | Sprint 3 | 04 Mar 2026 | 10 Mar 2026 | Add logging to all RAG operations for debuggability | Running full ingestion without checking sample output first | Incremental development (embed → index → query) | Added logging.INFO calls throughout rag_engine.py
4 | Sprint 4 | 11 Mar 2026 | 17 Mar 2026 | Unit-test each LLM prompt variant before finalizing | Hardcoding confidence thresholds — use config.py instead | Modular function design (_calculate_confidence, _suggest_kb_filename) | Moved all thresholds to .env via config.get_float_env()
5 | Sprint 5 | 18 Mar 2026 | 24 Mar 2026 | Write migration scripts alongside schema changes | Manual DB inspection — use proper test scripts | bcrypt for secure password storage | Created automated auth test in test_backend.py
6 | Sprint 6 | 25 Mar 2026 | 31 Mar 2026 | Break large orchestration functions into smaller helpers | Underestimating knowledge gap detection complexity | Using pandas for ticket data handling | Added 1-day buffer for complex features
7 | Sprint 7 | 01 Apr 2026 | 07 Apr 2026 | Prototype UI sketches before coding |  | Iterative UI development
8 | Sprint 8 | 08 Apr 2026 | 14 Apr 2026 | Add CI test run before final submission |  | Comprehensive documentation

## Legend
COLOUR LEGEND
| Green | Completed – Sprint/task fully done
| Yellow | In Progress – Currently active
| Grey | Planned – Upcoming, not started
| Blue | Alternating row highlight
| Salmon | Notes / Important information
Developer: Mohd Amaan Khan ¦ Project: AI Powered Smart Support & Ticket Resolution ¦ Start: 18 Feb 2026